## דרישות
ID | Module | Functional\None Functional | Description | Priority | Risk | Status | responsibility
1 | transport | NF | The system must support adding new truck with max weight, weight, plate number, drivers license needed, model | MH | Low | to be completed
2 | transport | F | The system must provide a document that contains amount of products that are delivered to the destination. This document will also have an id and the weight of the truck after being weighted | MH | Low | to be completed
3 | transport | NF | each delivery must be documented in the documentation management system | MH | Low | to be completed | Suppliers
4 | transport | F | The system can show the schedule deliverys for today | NTH | Low | to be completed | Suppliers
5 | transport | F | When adding a new driver, the system must inforce inserting a driving license type | MH | Low | to be completed
6 | transport |  | The system must have a weight of each potential product that the warehouse might order | NTH |  | to be completed
7 | transport | F | The system can show drivers type of license and name | NTH | Low | to be completed
8 | transport | F | The system can show truck's details such as truck max weight, weight, drivers license needed to drive | NTH | Low | to be completed
9 | transport | F | the system must support adding new site that must contain an area code address, contact number, contact name | MH | Low | to be completed
10 | transport | F | The system must support adding a new delivery, that contains source, destinations, truck number, driver,date, time of departure, delivery id, missing items in storage and amounts | MH | Low | to be completed
11 | transport | F | The system must provide an error if a truck is being weighted and the weight is above its maxweight. | MH | Low | to be completed
12 | transport | F | in a case of error because of overweight, the system must provide an alternative option: 1. replan this delivery 2. drop\change 1 of the destinations 3. switch truck 4. drop products the chosen option will be contained in the delivery document | MH | HIGH | to be completed
13 | transport | NF | The system must support receiving a document that contains missing products and amounts from the storage. It will contain also address of storage, from which supplier the product will be taken and the suppliers address | MH | HIGH | to be completed
14 | transport | F | In each new delivery, the system must show only available trucks, and relevant drivers (that are available, and have a correct drivers license) | MH | HIGH | to be completed
15 | transport | F | If there is a new delivery, the system will only show trucks that are available for that delivery date and time | MH | HIGH | to be completed
16 | transport | F | The system must show only drivers that are available for this truck, both because of license and shift availability | MH | Low | to be completed
17 | transport
18 | transport
19 | transport
20 | transport
21 | transport
22 | transport
23 | transport
24 | transport
25 | transport
26 | transport
27 | transport
30 | storage |  | each product in the system must have a weight.
31 | storage |  | each order that the delivery system receive, must contain each product with its amounts, and its weight. And a total weight of the order.

## טבלת שאלות פתוחות
number | Topic | Isuue
1 | truck issues | Does the system need to support selling\malfuncting trucks?
2 | independent suppliers | Can a Supplier that has its own delivery system, ask for our truck to deliver its products?
3
4
5
6
7
8
9
10
11

## UML
classes | inherits | depands on
Truck
site |  | supplier address, | shops address | contact name | contact number
delivery |  | status
deliverysys |  | main | מאגר ניהול הובלות | מסמך הובלה
drivers
order

## טבלת שאלות ותשובות
number | question | answer
1 | how to choose which driver and truck? | the system will show all available trucks, and the client who is using the system will choose which truck, then which driver if he is able to drive that truck
2 | where are all the trucks parked? | all trucks parked in the same place
3 | what type of trucks are available? | trucks that are more than 3.5 ton and less than 12 ton, and trucks that are more than 12 tons.
4 | what type of drivers license are available? | there are 2 drivers license: C,C1. C can drive all trucks, C1 can only drive the smaller trucks.
5 | how does the system engage a failure in a delivery? | the system will show an error if a failure acure due to a maxweight violation, and the user must create a new delivery.
6 | should the system prepare to an overweight incident? | Yes, the system can show the expected weight given from the suppliers
7
8
9
10
11

## משימות
הנחות | 1 | none | object diagram
דרישות |  | advanced
שאלות פתוחות |  | basic
טבלה בפורמט חופשי (שאלות-תשובות) |  | basic
תרשים מחלקות | 2 | basic
תרשים אובייקטים - 2 תרחישים | 3 | none
קוד | 4 | basic
הוראות לקוד | 5 | none
6

## main
ניהול משאיות | יצירת משאית
מחיקת משאית
יציאה
ניהול מסמכים | השג מסמך הובלה
השג מסמך יעד
יציאה
הוספת הזמנה | הוספת מוצר
מחיקת מוצר
עדכון כמות
סגירת הזמנה
יציאה
יצירת הובלה חדשה | תאריך, משאית, נהג | עדיין ריקה
עדכון הובלה | הוסף הזמנה
הצג הזמנות
הצג הזמנות לפי אזור
התחל הובלה
יציאה
הצגת הובלות
הצגת הובלות ממתינות
הצגת הובלות בתהליך
הצגת הובלות שהסתיימו
יציאה